## Test-Cases
Test Case ID | Test Case Description | Pre-Requisite | Step No | Step Description | Expected Result | Actual Result | Tested On | Tested By
Case 1 : Verification of Navigation to Vaccine Finder page
TC_P01 | Verification of Navigation to Vaccine Finder page | User should have a stable internet connection and browser | Step 1 | Open the desired browser(eg-Chrome, Firefox, IE) | Browser opened successfully | Browser opened successfully | 2024-09-05 | Nidhin Kumar
|  |  | Step 2 | Navigate to desired URL(https://indian-vaccine.web.app/) and verify whether the page is loaded or not | Navigated to Vaccine finder page successfully | Navigated to Vaccine finder page successfully
Scenario 1 : Validation in Vaccine Finder Page
Case 2 : Verification of Dropdown selections in Vaccine Finder page
TC_P02 | Verification of Dropdown selections in Vaccine Finder page | User should be on Vaccine Finder page url | Step 1 | Click on the 1st Dropdown option and validate the dropdown selection options | Dropdown options visible successfully for the 1st dropdown | No Dropdown options visible and identified as a defect | 2024-09-05 | Nidhin Kumar
|  |  | Step 2 | Click on the 2st Dropdown option and validate the dropdown selection options | Dropdown options visible successfully for the 2nd dropdown | No Dropdown options visible and identified as a defect
Case 3 : Verification of Radio buttons in Vaccine Finder page
TC_P03 | Verification of Radio buttons in Vaccine Finder page | User should be on Vaccine Finder page url | Step 1 | Navigate to the 1st radio button which signifies Recent Current Search and click on the button by selecting it | Radio button selected successfully | Radio button not selected successfully & identified as a bug | 2024-09-05 | Nidhin Kumar
|  |  | Step 2 | Place the mouse pointer on the 1st radio button and verify whether the name pops up in the side | "Recent Current Search" name appears on the side successfully | "Recent Current Search" name appears on the side successfully
|  |  | Step 3 | Navigate to the 2nd radio button which implies Refresh option and click on the button | Radio button selected successfully | Radio button not selected successfully & identified as bug
|  |  | Step 4 | Place the mouse pointer on the 2nd radio button and verify whether the name pops up in the side | "Refresh" name appears on the side successfully | "Refresh" name appears on the side successfully
|  |  | Step 5 | Navigate to the 3rd radio button which implies Notification option and click on the button | Radio button selected successfully | Radio button selected successfully
|  |  | Step 6 | Place the mouse pointer on the 2nd radio button and verify whether the name pops up in the side | "Notification" name appears on the side successfully | "Notification" name appears on the side successfully
Case 4 : Verification of About & Refresh options in Vaccine Finder page
TC_P04 | Verification of About & Refresh options in Vaccine Finder page | User should be on Vaccine Finder page url | Step 1 | Navigate to the About option and click on it and verify whether a popup appears with a hyperlink and name of the developer on it | Alert box visble successfully with the required details | Alert box visble successfully with the required details | 2024-09-05 | Nidhin Kumar
|  |  | Step 2 | Click on the hyperlink( Name of the developer) and verify whether we are redirected to the link on new tab | Redirected to the link on the new tab | Redirected to the link on the new tab
|  |  | Step 3 | Click on the hyperlink( Cowin API Guidelines) and verify whether we are redirected to the link on new tab | Redirected to the link on the new tab | Redirected to the link on the new tab
|  |  | Step 4 | Navigate back to the alert pop-up & Click on the cancel option on the bottom right corner of alert popup | Alert box closed successfully | Alert box closed successfully
|  |  | Step 5 | Navigate back to the alert pop-up & Click on the on the Cross sign on the right top corner of the alert popup | Alert box closed successfully | Alert box closed successfully
|  |  | Step 6 | Navigate back to the alert pop-up & Click outisde the alert pop-up and click on the Refresh option | Alert box closed & the Search results on the page should get refreshed successfully | Selection results not getting refreshed since there is no results. Identified as a bug
Scenario 2 : Validation in Covid Cases Tab
Case 5 : Verification of Dropdown selections in Covid Cases tab
TC_P05 | Verification of Dropdown selections in Covid Cases tab | User should be on Covid cases tab | Step 1 | Click on the 1st Dropdown option and validate the dropdown selection options | Dropdown options visible successfully for the 1st dropdown | No Dropdown options visible and identified as a defect | 2024-09-05 | Nidhin Kumar
|  |  | Step 2 | Click on the 2st Dropdown option and validate the dropdown selection options | Dropdown options visible successfully for the 2nd dropdown | No Dropdown options visible and identified as a defect
Case 6 : Verification of 3 Radio buttons in Covid Cases tab
TC_P06 | Verification of 3 Radio buttons in Covid Cases tab | User should be on Covid cases tab | Step 1 | Navigate to the 1st radio button on the right corner which signifies Text and click on the button by selecting it | Radio button selected successfully | Radio button selected successfully | 2024-09-05 | Nidhin Kumar
|  |  | Step 2 | Veirfy the search results (Active,Confirmed,Deceased,Recovered) | Search results appeared successfully as expected | Search results appeared successfully as expected
|  |  | Step 3 | Place the mouse pointer on the radio button and verify whether the name pops up in the side | "Text" name appears on the side successfully | "Text" name appears on the side successfully
|  |  | Step 4 | Navigate to the 2nd radio button from the right corner which signifies Pie Chart and click on the button by selecting it | Radio button selected successfully | Radio button selected successfully
|  |  | Step 5 | Veirfy the search results (Active,Confirmed,Deceased,Recovered) | Search results appeared successfully as expected | Search results appeared successfully as expected
|  |  | Step 6 | Place the mouse pointer on the radio button and verify whether the name pops up in the side | "Text" name appears on the side successfully | "Text" name appears on the side successfully
|  |  | Step 7 | Navigate to the radio button on the left side which implies Refresh option and click on the button | Radio button selected successfully | Radio button not selected & identified as a defect
|  |  | Step 8 | Place the mouse pointer on the radio button and verify whether the name pops up in the side | "Refresh" name appears on the side successfully | The search results in the page does not get refreshed & the name does not appear on the side and identified as a defect .
Case 7 : Verification of About option in Covid Cases tab
TC_P07 | Verification of About option in Covid Cases tab | User should be on Covid cases tab | Step 1 | Navigate to the About option and click on it and verify whether a popup appears with a hyperlink and name of the developer on it | Alert box visble successfully with the required details | Alert box visble successfully with the required details | 2024-09-05 | Nidhin Kumar
|  |  | Step 2 | Click on the hyperlink( Name of the developer) and verify whether we are redirected to the link on new tab | Redirected to the link on the new tab | Redirected to the link on the new tab
|  |  | Step 3 | Navigate back to the Alert popup & Click on the hyperlink( Cowin API Guidelines) and verify whether we are redirected to the link on new tab | Redirected to the link on the new tab | Redirected to the link on the new tab but page error
|  |  | Step 4 | Navigate back to the alert pop-up & Click on the cancel option on the bottom right corner of alert popup | Alert box closed successfully | Alert box closed successfully
|  |  | Step 5 | Navigate back to the alert pop-up & Click on the on the Cross sign on the right top corner of the alert popup | Alert box closed successfully | Alert box closed successfully
|  |  | Step 6 | Navigate back to the alert pop-up & Click outisde the alert pop-up | Alert box closed successfully | Alert box closed successfully
Scenario 3 : Validation in Download Certificate Tab
Case 8 : Verification of Download certificate option
TC_P08 | Verification of Download certificate option | User should be on Download Certificate tab | Step 1 | Click on the Download certificate option and verify whether a alert box appears for the action performed with heading "Download Certificate in Whatsapp" | Alert box visble successfully with the required details | Alert box visble successfully with the required details | 2024-09-05 | Nidhin Kumar
|  |  | Step 2 | Verify whether the Alert box contains the required details , hyperlink to open whatsapp | Alert box visble successfully with the required details | Alert box visble successfully with the required details
|  |  | Step 3 | Click on the "whatsapp link" hyperlink and verify whether we are navigated to the specified url in new tab | Navigated to the Specified url successfully | Navigated to the Specified url successfully
|  |  | Step 4 | Navigate back to the alert pop-up & Click on the cancel option on the bottom right corner of alert popup | Alert box closed successfully | Alert box closed successfully
|  |  | Step 5 | Navigate back to the alert pop-up & Click on the on the Cross sign on the right top corner of the alert popup | Alert box closed successfully | Alert box closed successfully
|  |  | Step 6 | Navigate back to the alert pop-up & Click outisde the alert pop-up | Alert box closed successfully | Alert box closed successfully